## Instructions
INSTRUCTIONS- READ FIRST- then fill out 'Project GANTT' sheet
Number | Work packages (WP), Activity, Deliverable (D) and Milestone (M) Titles | Activity Lead | Involved Participants | Start Date | End Date | 2026 |  |  |  | 2027
[6 empty] | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| WP 1 Project management and coordination |  |  | DD.MM.YY | DD.MM.YY
1.1 | Project management | [Name of institution] | [Name of all involved institutions] | 2027-02-01 | 2029-01-31
1.2 | Dissemination and communication | [Name of institution] | [Name of all involved institutions] | 2027-12-01 | 2029-01-31 | bar: 2026 11 to 2026 12; 2027 6
M1.1 | Project meetings | [Name of institution] | [Name of all involved institutions] | 2027-02-01 | 2029-01-31 | bar: 2026 9; 2026 11; 2027 1; 2027 3; 2027 5; 2027 7; 2027 9; 2027 11
M1.2 | Final conference | [Name of institution] | [Name of all involved institutions] |  | 2028-10-31
D1.1 | Progress reports | [Name of institution] | [Name of all involved institutions] | 2027-07-01 | 2027-01-31 | bar: 2026 12; 2027 6; 2027 12
WP 2 Lab experiment 1
2.1 | Selection of targets | [Name of institution] | [Name of all involved institutions] | 2027-02-01 | 2027-05-30
2.2 | Test of method 1 | [Name of institution] | [Name of all involved institutions] | 2027-05-01 | 2027-08-31
2.3 | Test of method 2 | [Name of institution] | [Name of all involved institutions] | 2027-07-01 | 2027-10-31 | bar: 2026 9
D2.1 | Data published in database | [Name of institution] | [Name of all involved institutions] |  | 2027-10-31 | bar: 2026 9
M2.1 | Select 5 targets for in vitro platform | [Name of institution] | [Name of all involved institutions] |  | 2027-05-30
M2.2 | Select method to be used | [Name of institution] | [Name of all involved institutions] |  | 2027-10-31 | bar: 2026 9
WP 3 Set-up of in vitro platform
3.1 | Set-up of in vitro platform | [Name of institution] | [Name of all involved institutions] | 2027-07-01 | 2028-11-30 | bar: 2026 9 to 2026 10
3.2 | Test of 5 targets | [Name of institution] | [Name of all involved institutions] | 2027-11-01 | 31.09.28 | bar: 2026 10 to 2027 8
M3.1 | Selection of 3 targets | [Name of institution] | [Name of all involved institutions] |  | 31.09.28 | bar: 2027 8
D3.1 | Data submitted in open-access paper | [Name of institution] | [Name of all involved institutions] |  | 01.01.29 | bar: 2027 12
WP 4
Activity 1
Activity 2
Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3
Save and Upload to Application as PDF:
On the Project GANTT sheet: Select File - Print.
In PRINT settings:
Choose a PDF printer (e.g. Adobe, Microsoft)
Select 'Print Active Sheets'
Landscape Orientation, A4
Select 'Narrow Margins'
Fit Sheet on One Page (If you have many rows of text, it may be better to 'Fit All Columns on One Page' and print across 2 pages)
State the title of each WP. WP1 should be project management.
You can add and delete Work Packages/activities as needed.
Milestones mark important events. Schedule enough project meetings to ensure involvement of all applicants and company partners.
Deliverables can be e.g., reports, datasets and publications.
Visualize the timeline for individual activities like this.
Milestones and Deliverables might only have end-dates.
Milestones (M) and Deliverables (D) must be derived from a specific activity in the work package.
Sept. 2026 is the first month that you start your project.

## Project GANTT
Number | Work packages (WP), Activity, Deliverable (D) and Milestone (M) Titles | Activity Lead | Involved Participants | Start Date | End Date | 2026 |  |  |  | 2027
[6 empty] | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 11 | 12
| WP 1 Project Management and Coordination |  |  | DD.MM.YY | DD.MM.YY
1.1 | Activity 1
1.2 | Activity 2
1.3 | Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3
WP 2 name
2.1 | Activity 1
2.2 | Activity 2
2.3 | Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3
WP 3 name
Activity 1
Activity 2
Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3
WP 4 name
Activity 1
Activity 2
Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3
WP 5 name
Activity 1
Activity 2
Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3
WP 6 name
Activity 1
Activity 2
Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3
WP 7 name
Activity 1
Activity 2
Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3